## Wx
PROJECT REPORT
Group | Group 5
Week | 12/9/2022 - 19/9/2022
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Chooses project topic | Completed | Team and mentor come to an agreement of which topic should team choose for capstone project
2 | Kicks off meeting | Completed | Meet up with team members
3 | Meets up with instructor | Completed | Introduce team with mentor
4 | Determine role of team members | Completed | Decide skills and strengths of each team member
5 | Registers capstone project | Completed | Reregisters capstone project with Trainning Department
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Team member meeting | All Team | Everyone meets each other and inform their skills set and position for the upcomming project capstone
2 | Decides team rules and regulations | All Team | Sets out working rules and regulation upon agreements of everyone
3 | Brainstorms project capstone ideas | All Team | Finds idea for project capstone topic
4 | Defenses project ideas against mentor's questions | All Team | Rules out which are good idea and which are not
5 | Choose final project idea | All Team | Chooses final project idead as project capstone topic
6 | Email Specialist of Trainning Department | VietNH | Registers capstone project with Representative of Trainning Department
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Develop Project Introduciton | 19/9/2022
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
Note on C5: Author: Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on C24: Author: Pending: issue occurred, no solution yet In Progress: occurred and handling issue Completed: occurred and handled issue