## Wx
PROJECT REPORT
Group | Group 5
Week | 20/9/2022 - 27/9/2022
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Creates survey form | Completed | Using survey to understand users background and their need of our system
2 | Develops project introduction | In Progress | Document survey information
3 | Publishs survey form online to survey users | In Progress | The goal is to survey 50 users
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Decides goals and objectives of survey | DucHM
2 | Brainstorms survey question for actor anglers | All Team | Chooses questions carefully based on goals and objectives of the survey
3 | Brainstorms survey question for actor fishing spots owner | All Team
4 | Creates survey using Google Form | AnhND | Implements survey questions in google form
5 | Delivers survey form to facebook group | All Team | Posts survey form to facebook group where potential user can do the survey form
7 | Gathes statistic information from survey form | VietNH
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
1 | Not enough data because only few users actually did the survey | In Progress | Re-posts survey form again
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Develop project software management plan | /9/2022
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
Note on C5: Author: Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on C27: Author: Pending: issue occurred, no solution yet In Progress: occurred and handling issue Completed: occurred and handled issue